## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | jaspreet singh
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
|  | 2 | the game board to have a black background
|  | 3 | to login so I can play the game
|  | 4 | to control the snake mouvements
|  | 5 | to being able to turn the snake in four directions
|  | 6 | to use the arrow keys so I can play with one hand only
|  | 7 | the prey to appear in random position
|  | 8 | the snake to eat the prey
|  | 9 | the snake size to increse after eating prey
|  | 10 | the create a new prey if the snake eats an old one
|  | 11 | to win if the snake eats 10 preys
|  | 12 | to lose if the snake hits the board border

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | jaspreet singh (23854662)
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2 | 28.18%
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard |  | 10% |  | 80%
3.1.2 |  |  | GUI for login form |  | 100%
|  |  | GUI for winning |  | 0%
|  |  | GUI for loosing |  | 0%
3.2 |  | Build the game logic
3.2.1 |  |  | Login Logic |  | 100%
3.2.2 |  |  | Snake logic |  | 0% |  | 10%
3.2.3 |  |  | Prey logic |  | 0% |  | 10%
3.2.4 |  |  | Board logic |  | 0%
3.3 |  | Build the game ending logic
3.3.1 |  |  | win logic |  | 0%
3.3.2 |  |  | lose logic |  | 0%
4 | Test and deploy the game |  |  | 3 | 0%
4.1 |  | Test login logic |  |  | 100%
4.2 |  | Test snake logic |  |  | 0%
4.2.1 |  |  | test snake mouvements |  | 0%
4.2.2 |  |  | the snake grow when eating |  | 0%
4.2.3 |  |  | test snake eats the prey |  | 0%
4.3 |  | Test prey logic |  |  | 0%
4.3.1 |  |  | test prey creation |  | 0%
4.3.2 |  |  | test prey destuction |  | 0%
4.4 |  | Test win logic |  |  | 0%
4.5 |  | Test lose logic |  |  | 0%
5 | Document the game |  |  | 4 | 0%